## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Notes | Date started (actual date) | Date finished (actual date)
1 | Check the user level | As an administrator I want to see all of the existing student hierarchy so that I can determine if the current level architectures are reasonable | very high | 1 | The student hierarchy needs to represent all existing levels and the names of each level The student hierarchy needs to be presented in the form of a hierarchy tree The student hierarchy needs to be displayed in the middle of the interface and can be clearly displayed Make sure that the latest student hierarchy shown is up to date |  | 3.29 | 4.9
2 | Record modules studied | As a student I want to know all the studied modules | very high | 1 | A grade rights text should be displayed in the grade panel |  | 3.29 | 4.9
3 | Selecting curriculum and modules | As a student I want to select the curriculum of particular category So that I can find the curriculum I want effectively | very high | 1 | Verify that the category list is shown in the class search page for the student to choose Verify that curriculum of that particular category can be automatically shown once the student choose a category Verify that curriculum will be listed in a default order (eg. Chronologically) for the student to look through |  | 3.29 | 4.9
4 | Keyword Searching | As a end-user I want to search the curriculum by key words So that I can screen out the details I care about | very high | 1 | Verify that there is a search bar in the class page for the students to type in words. Verify that the relevant curriculum will be shown to the end-students once the user press “Search” button. |  | 3.29 | 4.9
5 | Check the student’s name | As an administrator I want to look up students by name or ID so that I can issue benefits to a specific user | high | 2 | Make sure the student the system finds is a student The name and ID can be queried in conjunction with other options as a filter criteria |  | 4.12 | 4.23
6 | Check the student’s level | As an administrator I want to look up students based on a specific level so that I can issue different benefits to different levels of students | medium | 2 | Multiple levels can be selected to query simultaneously The student level can be queried in conjunction with other options as a filter criteria |  | 4.12 | 4.23
7 | Check the student’s gender and issue benefits | As an administrator I want to look up students based on a given gender so I can issue benefits to all students of a certain gender on a special day | medium | 2 | The gender can be queried in conjunction with other options as a filter criteria |  | 4.12 | 4.23
8 | Sort the search result | As an administrator I want to sort the result by different standard so that I can easily find the result I'm interested. | high | 2 | The system can sort the result by cliking some button and show the sorted result quickly |  | 4.12 | 4.23
9 | Modify the information of student | As an administrator I want to modify the information fo student so that I can correct something wrong if any | high | 2 | The system will provide a table so that the administrator can modify the text |  | 4.12 | 4.23
10 | Check my own grade | As a student I want to be able to easily see my grade levels so that I can see what benefits are available to me | high | 2 | The grade level should be prominently displayed at the top of the screen |  | 4.12 | 4.23
11 | View the marks achieved and produce relevant calculations for various purpose (e.g. degree classification, GPA etc) | As a student I want to easily see my remaining grade time so that I can know when I need to top up next time and when my grade benefits expire | high | 2 | grade time remaining should be displayed next to the grade level |  | 4.12 | 4.23
12 | View grade rewards points | As a student I want to easily see my grade rewards points so that I can know how many points I have available | high | 2 | grade rewards points should be prominently displayed below the grade level Use a progress bar to display the current grade rewards points and the points required to reach the next level. |  | 4.12 | 4.23
13 | Sort the Portfolios result | As a student I want to sort the portfolios result so that I can find the things I'm interested easily | high | 2 | The system can sort the result by cliking some button and show the sorted result quickly |  | 4.12 | 4.23
14 | Sort the live session search result | As a student I want to sort the live session search result so that I can find the result easily | high | 2 | The system can sort the result by cliking some button and show the sorted result quickly |  | 4.12 | 4.23
15 | Contact Panel | As a student I want to submit some advice to the office so that I can help school do better | high | 3 | There should be a panel to input email, subject and content. Once the user click "submit", the will receive this message. |  | 4.12 | 4.23
16 | Adding curriculum | As an administrator I want to add curriculum to the platform provided for students So that I can enrich the content of the software for the students to enjoy | high | 3 | Verify that curriculum can be uploaded directly by the administrator through selecting files of operating system such as OS X, Windows Verify that the class overview picture can be randomly generated Verify that the administrator can fill in a table to complete the information of the class while uploading the class. |  | 4.26 | 5.14
17 | Modification of curriculum | As an administrator I want to modify the information of curriculum So that I can correct the information which is typed wrong before | high | 3 | Verify that there is a ‘gear’ icon for the administrator to press so that the administrator can enter the information modification page. |  | 4.26 | 5.14
18 | Rating | As a student I want to rate the curriculum So that I can recommend my preferred curriculum to all the other students of this software | medium | 3 | student can rate a class by score from 1 to 10 once after he/she watches the class. All the scores from a wide range of students will be used to generate the overall rating score for one class The rating score of a class will be shown under the class. |  | 4.26 | 5.14
19 | Favourite list | As a end-user I want to add some curriculum to my favourite list So that I can find them again easily when I want to watch them again, especially when I forget their titles. | medium | 3 | Verify that there is a star icon for the user to press so that the class can be added to the user’s favourite list Verify that the user can enter the favourite list in their personal page |  | 4.26 | 5.14
20 | likes | As a end-user I want to give likes to some curriculum So that I can encourage the class producer | medium | 3 | Verify that there is a thumb icon in the class page for students to choose. Verify that the number of likes can be shown in the class page. |  | 4.26 | 5.14
21 | history record | As a end-user I want to have a history record which keeps the curriculum that I’ve watched before So that I can look back to them later | medium | 3 | Verify that the system can record every browsing track of the user Verify that the browsing history can be found in the personal page. |  | 4.26 | 5.14
22 | add the live session to class list | As a student I want to add the live sessions that I have booked to my own class list. So that I can directly attend it every time I log in and enter personal home page | medium | 3 | Verify the student can add the live sessions into their class list. Verify after adding, the class list of students can change timely. Verify the student can check the class list in the home page. |  | 4.26 | 5.14
23 | Book the live session | As a student I want to booked the live session that I have selected. So that I can attend the corresponding lecture | high | 3 | Verify the student can see which classes can be choosn. Verify the student can book the live session and can receive notification if booked successfully. |  | 4.26 | 5.14
24 | grade expiration reminder | As a student I want to receive a timely reminder before the expiration of my grade so that I can keep my grade | high | 3 | An alert trigger should be displayed on the top of the user interface within three days remained |  | 4.26 | 5.14
25 | Open account | As an administrator I want to get the student's nickname, password, email, gender, and date of birth when they register their account so that I can open an account for a new student and enter the account information into the system | high | 3 | Verify that the student does not exist in system The student's height and weight information can be entered as optional information |  | 4.26 | 5.14
26 | search the live session based on personal plan | As a premier student I want to filter the live sessions based on my personal plan. For example, I can only attend the Yoga classes or strength classes. So that I can get more targeted training | medium | 3 | Verify the premier student can filter the live sessions based on their personal plan. |  | 4.26 | 5.14
27 | Import/export of data | As an administrator I want to see the monthly income of the grade fee so that I can assess how profitable our is | low | 4 | The bar chart shows the monthly income of grade fees in the past 12 months and the annual income of grade fees in the past three years |  | 5.17 | 5.21
28 | Commenting | As a student I want to comment on the curriculum So that I can share my ideas with other students, even I can make friends with them through the communication in the comment area. | medium | 4 | Verify that the user can type in the text filed under the class to send comment Verify that the text encoding of the comment support UTF-8, in other words, Chinese, English, Japanese and other languages all over the world will be supported. Verify that the user can see the comments sent by other students. |  | 5.17 | 5.21
29 | Birthday details | As a student I want to get extra discounts on my birthday so that I would be more willing to become a student | medium | 4 | - Make sure that only students can view such courses |  | 5.17 | 5.21
30 | Record achievements (e.g. awards, prizes and honours etc) | As a student I want to have live sports courses and action instructions recorded by coaches exclusively for students so that I can enjoy better exercise guidance after becoming a student | very low | 5 | students-only courses need to be presented uniformly in a specific interface |  | 5.24 | 5.28
31 | Record skills gained | As a professional trainer I want to know the hottest class in the recent days So that I can catch up with the trend | very low | 5 | Verify the watching history of one particular class can be recorded in the files. Verify the software can work out the hottest class in terms of the viewing times. Verify the hottest class can be shown in the main page or search page |  | 5.24 | 5.28
32 | add categories | As an administrator I want to add categories of training class to the software So that I can introduce a new way of training to my students | high | 5 | Verify that the administrator can add new category in the management page Verify that the newly added category can be searched by the end-students. |  | 5.24 | 5.28