## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Notes | Date started (actual date) | Date finished (actual date)
A Login page | A01 Distinguish between administrators and students | As a user, I want to select my identity on the landing page and enter the corresponding home page | very high | 1 | The system allows users to select an identity on the login page |  | 3.29 | 4.9
| A02 Login function | As a user, when we enter the correct account and password, the system will log in automatically | very high | 1 | The system can be successfully logged in |  | 3.29 | 4.9
| A03 Login error | As a student when we enter the wrong account or password, the system will automatically report an error, reminding us that there is a mistake, so that we can change the login account or password | very high | 1 | The system will report an error if you enter the wrong account number or password |  | 3.29 | 4.9
B Personal homepage | B01 The main page displays the class schedule | As a student, we can see the curriculum intuitively on the home page | very high | 1 | We can see a concise curriculum on the home page |  | 3.29 | 4.9
| B02 Home page message notification | As a student, I want to know the important notices recently so that I don't miss any important information | high | 2 | The system will prompt an important notification |  | 4.12 | 4.21
| B03 Multiple prompt bars on the main page | As students, we can select the service we want from the prompt bar on the home page and access it quickly | high | 2 | The home page offers a variety of service options |  | 4.12 | 4.21
| B04 The home page displays personal information | As students, we can see our personal information and photos on the home page | medium | 2 | The main page has general information about the students |  | 4.12 | 4.21
C Curriculum schedule | C01 Check schedule by week of school year | As students, on the schedule page, we can search for the schedule by year and week so that I can get the correct schedule quickly | high | 2 | The system provides a range of school years and weeks for students to inquire freely |  | 4.12 | 4.21
D Curriculum schedule | D01 Show the content and progress of course selection | As a student, I want to know the general content and course progress of the courses I choose so that I can learn better | high | 2 | The introduction of the course will be displayed |  | 4.12 | 4.21
| D02 Search course information | As a student, I want to know the basic information about a course so that I can decide whether to take it or not | high | 2 | The system will allow students to search for basic information about the course |  | 4.25 | 5.6
| D03 Demonstration-derived course | As a student, I want to export the course so that I can check it at any time | high | 2 | The system can provide export service of curriculum schedule |  | 4.25 | 5.6
E Grade management | E01 Query grades | As a student, I would like to check my grades of all the courses so that I can know how well I have mastered the knowledge | high | 2 | The system can query the corresponding course grades according to the students' information |  | 4.25 | 5.6
| E02 Sort the search result | As an administrator I want to sort the result by different standard so that I can easily find the result I'm interested. | medium |  | The system can sort the result by cliking some button and show the sorted result quickly |  | 4.25 | 5.6
| E03 Grades visualization | As a student, I want to have a clearer idea of my grades | medium | 2 | The system will provide a simple and clear way for students to view the results |  | 4.25 | 5.6
| E04 Grades analysis | As a student I want to be able to easily see my grade levels so that I can see what benefits are available to me | high | 2 | The system will analyze the student's score, including but not limited to the comparison with the previous semester and the average score of the course |  | 4.25 | 5.6
F Honor management | F01 Honor query | As a student, I want to know the honors I have received so that I can be more confident about myself | medium | 3 | The system will allow students to look up honours based on the academic year |  | 5.8 | 5.13
| F02 Honor show | As a student, I want to see my honor which will make me proud | high | 3 | The system displays all the honors the student has earned |  | 5.8 | 5.13
G Administrator module | G01 Administrator modified course | As an administrator, I want to revise students' courses at any time so that students can get the correct schedule | high | 3 | The system provides a way for administrators to modify student courses |  | 5.8 | 5.13
| G02 Administrator add score | As an administrator, I would like to add a missing course grade to the students | high | 3 | The system provides a way for administrators to increase course grades |  | 5.8 | 5.13
| G03 Administrator delete score | As an administrator, I would like to delete a student's grade for an invalid course | medium | 3 | The system provides a way for administrators to delete course grades |  | 5.8 | 5.13
| G04 Administrator modify grade | As an administrator, I want to revise students' grades at any time to ensure that students' grades are correct | high | 3 | The system provides a way for administrators to modify course grades |  | 5.8 | 5.13
| G05 Administrator modify honor | As an administrator, I want to keep updating students' honors and achievements so that when they receive new honors, they can quickly see them on the system | high | 3 | Administrators can modify student honors |  | 5.8 | 5.13
| G06 The administrator modifies and adds a user | As an administrator, I want to add accounts for new students so that they can learn | medium | 3 | The administrator can manage the student's account password |  | 5.8 | 5.13